IFRS 17 Game - Client Rollout Plan and March 2026 Timeline

Popularising IFRS17Game.com across KAFS client insurers + product enhancements

Prepared for: KAFS Leadership
Prepared by: Robin & Roseline
Date: 20 Jan 2026

# Executive Summary

This plan operationalises the CEO directive to (1) onboard ten KAFS client insurers onto IFRS17Game.com and (2) enhance the platform with an admin-managed question bank segmented into Standard, Tournament (Expert), and Non-technical/Beginner pathways, plus company-level leaderboards and email/certificate integration. The goal is to run repeatable, sponsor-led rollouts per insurer and close March with clear adoption evidence, engagement metrics, and a ready-to-scale playbook.

# Scope and Success Metrics

Client adoption: 10 insurers launched with a named sponsor, company code (or invite link) enabled, and at least one staff cohort onboarded.

Engagement: each launched insurer achieves a defined participation baseline (e.g., 30-200 users depending on size) and measurable activity (weekly active players, completion rates).

Product: admin question bank + segmentation, tournament-only questions workflow (AI draft + Leslie verification), company leaderboards, email and certificate automation.

Reporting: weekly snapshot to leadership covering participation, completion, average score, and top performers per company.

# Target Insurers

Top 10 (as primary March targets):

Kenya Reinsurance Corporation HQ

Jubilee Health Insurance Limited

Intra Africa Insurance Company Limited

Monarch Life Insurance Company Limited

Pioneer Insurance Company Limited

BUPA Global Insurance Limited

Old Mutual General Insurance Kenya Limited

AAR Insurance Kenya

Geminia Insurance Company Limited - Life

Monarch General Insurance Company Limited

Additional insurers (pipeline / optional if capacity allows):

Kenya Orient Insurance Company

Fidelity Shield Insurance Company Limited

The Heritage Insurance Company Limited

Alliance Insurance Limited

# Current Game Snapshot

The current IFRS 17 Game user experience includes a module-based learning path, a live leaderboard, player scoring (score, streak, level, combo), a timed question flow, and sign-in/sign-up gating for locked modules. This existing structure is a strong base for a company rollout model (company codes, company-only boards) and differentiated question sets by audience.

# Product Enhancements - Requirements and Acceptance Criteria

## 1. Admin Question Bank (Q&A Database)

Key requirements:

Admin can create, edit, archive questions and answers.

Each question is tagged by: (a) level (Beginner/Standard/Expert), (b) module/topic, and (c) status (Draft/Approved/Archived).

Bulk import/export (CSV/Excel) to accelerate population.

Acceptance criteria:

Admin portal lists questions with filters (level, module, status) and search.

Only Approved questions appear in gameplay.

## 2. Tournament-only Questions (Expert)

Key requirements:

AI-assisted drafting of tournament questions into Draft status.

Verification workflow where Leslie (or designated SME) approves questions/answers.

Acceptance criteria:

Tournament mode pulls only Approved Expert questions.

Audit trail: who approved and when.

## 3. Company-level Ranking (Company Leaderboards)

Key requirements:

Each player is associated with a company (via company code, invite link, or admin assignment).

Company-only leaderboard view, plus optional global leaderboard with filters.

Support for non-technical question set for broader staff competitions.

Acceptance criteria:

Company leaderboard shows rank, score, and basic stats for that company only.

Admin can create/manage companies and generate company codes/links.

## 4. Email and Certificates Integration

Key requirements:

Automated email notifications (welcome, reminders, completion).

Certificate issuance triggered by completion and/or score threshold.

Optional weekly sponsor summary email (participation and top performers).

Acceptance criteria:

Certificate can be generated and delivered reliably to player email.

Basic email templates are configurable (branding, signatures).

# Question Bank Assessment (Sample File Review)

The provided sample question file contains 217 questions across multiple IFRS 17 modules. Complexity distribution: Standard (118), Beginner (51), Expert (48). This is a good starting balance for a segmented game experience, but the rollout will benefit from (a) consistent module naming, (b) explicit topic tags (CSM, RA, PAA, LoA etc.), and (c) an approval workflow for Expert/Tournament content.

Questions by module and complexity:

| Module | Beginner | Standard | Expert |
| --- | --- | --- | --- |
| Combination & Separation of Insurance Contracts | 0 | 6 | 5 |
| Discounting CSM and Risk Adjustment | 2 | 11 | 2 |
| IFRS 17 Fundamentals | 6 | 7 | 0 |
| Insurance Finance Income or Expenses | 0 | 7 | 8 |
| Insurance Service Result | 0 | 12 | 3 |
| Investment Contracts with Discretionary Participation Features | 3 | 10 | 3 |
| Level of Aggregation | 4 | 6 | 5 |
| Measurement on Initial Recognition | 7 | 6 | 2 |
| Modification and Derecognition of Insurance Contracts | 5 | 9 | 3 |
| Onerous Contracts | 4 | 8 | 3 |
| Premium Allocation Approach | 2 | 11 | 2 |
| Presentation in the Statement of Financial Position | 3 | 5 | 2 |
| Recognition of Insurance Contracts | 5 | 5 | 5 |
| Reinsurance Contracts Held | 4 | 9 | 2 |
| Subsequent Measurement | 6 | 6 | 3 |

Recommendations to strengthen the question database:

Enforce a unique question ID and track version history (important for tournament updates).

Add fields: topic tag, difficulty (1-5), IFRS reference/paragraph (optional), and last reviewed date.

Standardise module names to match the game UI exactly to avoid mapping issues.

Adopt a Draft -> Approved workflow, especially for Expert questions verified by Leslie.

# Client Rollout Tracker

Use the tracker below to manage outreach, sponsor alignment, launch readiness, and post-launch reporting per insurer.

Status labels (suggested):

Not Started

Contact Identified

Intro Sent

Discovery Scheduled

Discovery Done

Launch Scheduled

Launch Live

In Progress

Completed

On Hold

| Insurer | Primary Sponsor (Client) | KAFS Owner | Client Segment | Launch Format | Company Code / Board | Status | Next Action | Target Week (March) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Kenya Reinsurance Corporation HQ |  | Roseline (Client) / Robin (Product) | IFRS 17 specialists + finance | Guided (first cohort) | Required | Not Started | Identify sponsor; send intro; book 30-min demo | Wk2 |
| Jubilee Health Insurance Limited |  | Roseline (Client) / Robin (Product) | Mixed (IFRS 17 + broader staff) | Guided (first cohort) | Required | Not Started | Identify sponsor; send intro; book 30-min demo | Wk2 |
| Intra Africa Insurance Company Limited |  | Roseline (Client) / Robin (Product) | Mixed (IFRS 17 + broader staff) | Guided (first cohort) | Required | Not Started | Identify sponsor; send intro; book 30-min demo | Wk3 |
| Monarch Life Insurance Company Limited |  | Roseline (Client) / Robin (Product) | IFRS 17 specialists + finance | Guided (first cohort) | Required | Not Started | Identify sponsor; send intro; book 30-min demo | Wk3 |
| Pioneer Insurance Company Limited |  | Roseline (Client) / Robin (Product) | Mixed (IFRS 17 + broader staff) | Guided (first cohort) | Required | Not Started | Identify sponsor; send intro; book 30-min demo | Wk3 |
| BUPA Global Insurance Limited |  | Roseline (Client) / Robin (Product) | Mixed (IFRS 17 + broader staff) | Guided (first cohort) | Required | Not Started | Identify sponsor; send intro; book 30-min demo | Wk4 |
| Old Mutual General Insurance Kenya Limited |  | Roseline (Client) / Robin (Product) | Mixed (IFRS 17 + broader staff) | Guided (first cohort) | Required | Not Started | Identify sponsor; send intro; book 30-min demo | Wk4 |
| AAR Insurance Kenya |  | Roseline (Client) / Robin (Product) | Mixed (IFRS 17 + broader staff) | Guided (first cohort) | Required | Not Started | Identify sponsor; send intro; book 30-min demo | Wk4 |
| Geminia Insurance Company Limited - Life |  | Roseline (Client) / Robin (Product) | IFRS 17 specialists + finance | Guided (first cohort) | Required | Not Started | Identify sponsor; send intro; book 30-min demo | Wk5 |
| Monarch General Insurance Company Limited |  | Roseline (Client) / Robin (Product) | Mixed (IFRS 17 + broader staff) | Guided (first cohort) | Required | Not Started | Identify sponsor; send intro; book 30-min demo | Wk5 |

Pipeline insurers (optional):

| Insurer | KAFS Owner | Status | Notes |
| --- | --- | --- | --- |
| Kenya Orient Insurance Company | Roseline | Not Started | Add if capacity allows |
| Fidelity Shield Insurance Company Limited | Roseline | Not Started | Add if capacity allows |
| The Heritage Insurance Company Limited | Roseline | Not Started | Add if capacity allows |
| Alliance Insurance Limited | Roseline | Not Started | Add if capacity allows |

# Tight March 2026 Timeline (Week-by-Week)

This timeline assumes prerequisite prep is completed by end-Feb (launch kit ready, company leaderboard feature in progress, and question bank import path confirmed). If any prerequisites slip, prioritise pilot launches while completing the remaining feature work in parallel.

## Pre-March prerequisites (complete by 28 Feb 2026):

Confirm the 10 target insurers and primary contacts per insurer.

Prepare the Client Launch Kit (1-pager, sponsor guide, staff invite email templates).

Create admin question bank import format; load the provided question set and validate mappings.

Define certificate trigger (completion and/or score threshold) and email templates.

Agree on company leaderboard design (company-only board + optional global filter).

## Week 1 (02 Mar 2026 - 08 Mar 2026)

Run outreach sprint: send intro to all 10 sponsors; secure discovery/demo meetings (30 minutes).

Finalize rollout mechanics: company codes/invite links; sponsor dashboard view; reporting template.

Lock pilot companies (2) and schedule launch windows.

## Week 2 (09 Mar 2026 - 15 Mar 2026)

Launch pilots (2 insurers): guided onboarding + 7-14 day challenge kickoff.

Collect early feedback (UI friction, question clarity, leaderboard expectations).

Leslie begins verification of Expert/Tournament question set; approve first batch.

## Week 3 (16 Mar 2026 - 22 Mar 2026)

Launch wave 1 (3 insurers): reuse playbook, automate comms, and track metrics.

Implement/enable company-only leaderboards for launched insurers.

Publish weekly sponsor summary emails for pilots + wave 1.

## Week 4 (23 Mar 2026 - 29 Mar 2026)

Launch wave 2 (3 insurers): continue cadence; address any support tickets within 24 hours.

Complete tournament workflow and enable tournament-only mode for IFRS 17 specialists where needed.

Mid-month leadership update: progress vs target and engagement metrics.

## Week 5 (30 Mar 2026 - 31 Mar 2026)

Launch final wave (2 insurers) and close out March reporting.

Produce final March pack: adoption evidence per insurer, engagement metrics, lessons learned, and April scale plan.

Confirm next quarter expansion targets (additional pipeline insurers).

# Governance and Weekly Cadence

Weekly 30-minute internal stand-up (Robin + Roseline + Leslie): track outreach, launches, blockers, and product items.

Weekly sponsor update email per launched insurer: participation, completion, and top performers.

Single source of truth tracker (shared sheet) updated daily during March.

Escalation path: Roseline -> Robin -> CEO sponsor for non-responsive clients or decision delays.